# Stage 8 — Submission Checklist

Thesis: Digital Media vs Dawn Newspaper: A Comparative Political Discourse Analysis of the Coverage of the 26th Constitutional Amendment

Researcher: Muhammad Khan · Supervisor: Khuram Dad · Session: 2026

Checked on: 14 October 2026

Overall status: ❌ NOT READY FOR SUBMISSION. Chapters 1–3 are drafted; the analysis (Chapter 4), the findings (Chapter 5), the abstract and several preliminary pages depend on data that has not yet been collected.

Key: ✅ done · 🟡 partly done / needs confirmation · ❌ not done · ⏸ blocked (waiting for something)

## A. University and departmental requirements

Sources: D1 = Thesis Format (2024); D2 = supervisor's "BS English Thesis (9081)" slides; D3 = APA 7th guide.

### A1. Formatting (D1)

| # | Requirement | Status | Notes |
| --- | --- | --- | --- |
| 1 | Typed on computer | ✅ | Word file produced |
| 2 | Times New Roman, 12 pt | ✅ | Applied in Word file |
| 3 | Double spacing | ✅ | Tables single-spaced (APA allows this; confirm with supervisor) |
| 4 | Margins: 2" left, 1" elsewhere | ✅ | Confirmed by researcher |
| 5 | One space after punctuation | ✅ |  |
| 6 | First-line indent 0.5" | ✅ |  |
| 7 | Page numbers top right, 0.5" from top | ✅ |  |
| 8 | Roman numerals for preliminary pages; title page = i, not printed | ✅ | Set up in Word file |
| 9 | Italics for titles of works (e.g. Dawn) | ✅ | Checked in Stage 7 |
| 10 | Chapter heading "CHAPTER 1" + title, 14 pt bold centred | ✅ |  |
| 11 | Level 1 headings 14 pt centred; Level 2 headings 12 pt flush left | 🟡 | Applied as I read the rule; supervisor to confirm |
| 12 | Title in title case, bold, centred, upper half of page | ✅ | Placeholder title page |

### A2. Preliminary pages (D1, D2)

| # | Page | Status | What is needed |
| --- | --- | --- | --- |
| 13 | Title page | 🟡 | Placeholder only. Need official AIOU/department template |
| 14 | Candidate Declaration Form (16 pt bold heading) | ❌ | Need the official form. It must be signed by you personally after the work is complete. Claude will not write or sign it |
| 15 | Acknowledgement | ❌ | You should write this in your own words (optional per D2). I can correct the English |
| 16 | Dedication | ❌ | Optional; your own words |
| 17 | Abstract: one paragraph, ≤250 words, no indent, topic + RQs + data + method + analysis + results + conclusion; 5–6 italic keywords | ⏸ | Needs findings. Written last |
| 18 | Table of Contents | 🟡 | Automatic field in Word; update before printing |
| 19 | List of Tables | ❌ | Tables 3.1, 3.2 exist; Ch. 4 tables to come. Placement to confirm (front or after Ch. 5) |
| 20 | List of Figures | — | Not needed unless figures are added |
| 21 | List of Abbreviations | ❌ | To prepare: CDA, CJP, ICJ, JCP, JUI-F, NA, PML-N, PPP, PTI, RQ. Placement to confirm |
| 22 | Supervisor certificate | — | Not required by any document; add only if the department supplies one |

### A3. Main body (D1, D2)

| # | Requirement | Status | Words |
| --- | --- | --- | --- |
| 23 | Ch. 1 Introduction with all required headings | ✅ draft | ≈1,690 |
| 24 | Ch. 2 Literature Review: theory, previous research, research gap; analytical, not descriptive | 🟡 draft | ≈2,450 |
| 25 | Ch. 3 Methodology with all required headings | 🟡 draft (present tense; update after collection) | ≈1,790 |
| 26 | Ch. 4 Data Analysis and Discussion, organised by RQ, answering all RQs | ⏸ template only | 0 |
| 27 | Ch. 5 Findings, Conclusions, Recommendations; no new data | 🟡 partial | ≈450 |
| 28 | Minimum 10,000 words | ❌ | ≈6,380 now |

### A4. Citation and references (D1 §5, D3)

| # | Requirement | Status | Notes |
| --- | --- | --- | --- |
| 29 | APA 7th edition in-text and reference list | ✅ | Formatted in APA 7 |
| 30 | Every citation in reference list and vice versa | ✅ | Checked in Stage 7 (28 references) |
| 31 | All bibliographic details verified | 🟡 | 16 [VERIFY] items outstanding |
| 32 | Direct quotations have page/paragraph numbers | ✅ so far | No direct quotations from literature yet; corpus quotations will use "para." |
| 33 | No unverifiable or invented sources | ✅ | 3 doubtful sources rejected in Stage 4 |

### A5. Supervisor's final checklist (D2, slide 30)

| Item | Status |
| --- | --- |
| Five chapters complete | ❌ (Ch. 4 and most of Ch. 5 missing) |
| APA 7th edition followed | ✅ |
| Research gap identified | ✅ (provisional until full texts are read) |
| Objectives and questions aligned | ✅ |
| Methodology explained | ✅ |
| Findings discussed | ⏸ |
| References complete | 🟡 (verification pending) |
| Declaration of originality included | ❌ (needs official form; signed by you) |

## B. Research integrity checks

| # | Check | Status |
| --- | --- | --- |
| 34 | No invented sources, quotations, data or findings | ✅ So far. All placeholders are labelled |
| 35 | Findings in [ABSTRACT ONLY] passages checked against full texts | ❌ 11 passages |
| 36 | Corpus texts collected, archived and logged (Appendix A) | ⏸ |
| 37 | Coding sheets completed for all 16 texts (Appendix B) | ⏸ |
| 38 | Methodology tense changed to past after collection | ⏸ |
| 39 | All [UPDATE AFTER …] markers resolved | ⏸ 4 |
| 40 | All highlighted markers removed from final file | ❌ |
| 41 | AI-assistance disclosure | 🟡 Ask your supervisor whether AIOU or the department requires you to declare use of AI tools. Policies differ; follow theirs |
| 42 | Plagiarism/similarity check (e.g. Turnitin), if the university uses one | ❌ Ask the department |

## C. Decisions still needed from you or your supervisor

| # | Question | Who decides |
| --- | --- | --- |
| Q1 | Official title-page template and declaration form | Department |
| Q2 | Lists of Tables/Abbreviations: front pages or after Chapter 5? | Supervisor |
| Q3 | Heading sizes as applied: correct? | Supervisor |
| Q4 | Does the 10,000-word minimum exclude references and appendices? | Supervisor |
| Q5 | Title page: AIOU only, or college name too? | Supervisor |
| Q6 | Supervisor's name spelling: "Khuram Dad" or "Khuram Daad"? | You |
| Q7 | Approval of the refined title and scope (26th Amendment; The Current + Voicepk.net; 16 texts) | Supervisor — most urgent |
| Q8 | AI-use disclosure requirement | Supervisor/department |
| Q9 | Submission deadline, number of copies, binding and viva date | Department |

## D. Path to submission (in order)

| Step | Task | Who | Unlocks |
| --- | --- | --- | --- |
| 1 | Show the Word file (Ch. 1–3) to the supervisor; get answers to Q2–Q5, Q7–Q9 | You | Confidence that the scope is approved |
| 2 | Collect the 16 articles (Stage 3 plan, §4), or enable news-site access | You (or me, if access is enabled) | Chapter 4 |
| 3 | Upload the 4 Pakistani journal PDFs | You | Removing [ABSTRACT ONLY] in Ch. 2 |
| 4 | Analyse the corpus; write Chapter 4 | Me, with your review | ≈4,000 words |
| 5 | Complete Chapter 5 (§5.2–5.5) from Chapter 4 | Me | ≈850 words |
| 6 | Resolve all [VERIFY] items; finish Ch. 2 | Me (with library access by you where needed) | Clean references |
| 7 | Write the abstract; prepare lists; insert official title page and declaration | Me + you (declaration, acknowledgement and dedication are yours) | Preliminary pages |
| 8 | Full Stage 7 edit of the complete thesis; rebuild Word file | Me | Final draft |
| 9 | Supervisor's final review; similarity check; sign declaration | You | Submission |
| 10 | Viva preparation: practise explaining every decision | You, with me | Defence |